## SOA Team Weekly Status Report
SOA Team
Weekly Status Report as of Oct 25, 2019
S.No | Project | Start Date | Completion Date | Resource | Tasks Accomplished
1 | BT_2358 - IDAM/SOA enhancements |  |  | Sandeep | OSB wrapper service implementation for json to xml transformation, service testing with different type of payload, table configuration for outbound file. JSON data polling and creation of file data SOA POC development started, OSB generic service sales force get data issue work due to chunk read JSON to FTP file POC publish POC development, SOA service configuration Xquery developement to prepare file data based on JSON data fetched from Sales force VAM POC configuration for different object, end to end process testing with new inbound & outbound object
|  |  |  | Rama | JSON to FTP file POC publish POC development, SOA service configuration
|  |  |  | Malla | SFDCEBSIntegration: understanding flow from SalesForce to EBS. Worked on sales force objects. Developed SFProjectPub and deployed into Dev Did tested SFDC to EBS flow.
|  |  |  | Kanifnath | Analyze the service to add the CTI Graduate field in GRM and CMQA.
|  |  |  | Shrikant | 1. identifying the GSK production issue and helping tony to understand the data flow. 2. helped in identifyng the issue with REMOVE operation.
2 | 7006517 - GSK CH BDM – 212224 Smile |  |  | Shivang | * Took compensatory off on Monday in lieu of worked some on Sunday. * Since tony escalated all pending issue to Oracle, there was no work from Gsk. Hence went through EDC Mapper codeBase for Understanding. * Tony asked to look into Gsk-SOA code and verify if duplicate query issue is from our end or not. Hence went through code and find out that we not create duplicate query from our end. * Had a discussion with Shrikant on duplicate query, he stated that we cannot have duplicate query created until n unless Inform do changes in query. There can be case where Inform raises or do changes for same query again n again.
3 | BT_184_L - Vault Config eTMF & Doc Gtwy |  |  | Shashi | IQOQ for person object migration in PKEN3O
RFC Created for Person object and veeva enhancement migration in PKEN3O
Person Object change code migration in Test
End to end testing of veeva integration in staging environment
|  |  |  | Kanif | VeevaUserSub service developed for person object changes without OID and OIM implementation. Deployed the service on Dev environment as well as Test Environment. Perform testing for all possible scenarios and generate screenshots for IQOQ document. Generated jar and configuration plan Production Server deployment
4 | BT_2347 - Subject Data Transfer Services |  |  | Shrikant | 1. RaveSTS DB configuration call with Sri and configuring all the required data in DB for Galderma study. 2. Rave_sts_transactions proc debug with nash. 3.Testing RaveSTS Services end to end after configurations for Galderma Study. 4. Fixing the bugs and issue found after study for Galderma study and changed the artifacts in Resource repository OSB service . 5. Testing after bug fixes for all transaction where study_event_oid = "SUBJECT" and got sucess in posting the data. 6.Worked on debugging the stored procs for the other study_event_oid. 7.Configuration of Galderma-69 study in database and creating the transformation for this study. 8. Documenting the configuration done for new study in RaveSTS and inset script for db whenever a new study comes in.
5 | BT 1778 GB Users |  |  | Malla | . Modified GBUser seriiuve for capture business error
6 | BT_2433 - Assoc Mgmt Implement:Phase 1 |  |  | Shivam | Redeveloped EBSProjectSub and deployed on Dev server. Perform end to end testing of services. Created activiry diagram for SFProjectPub, EBSProjectSub, EBSProjectStatusPub, SFEBSProjectStatusSub. Created Sequence Diagram for SFProjectPub, EBSProjectSub, EBSProjectStatusPub and Check-in on GIT.
7 | BT_2569 - Update PRims and Reltio Interfaces |  |  | Simrat | Made Changes to Reltio interfaces which includes the following: 1. Adding Changes to Source and Target Schemas. 2. Making changes to transformations present in the interfaces. 3. Adding Rest adapter to Call out Udpate Investigator operation instead of create investigator 4. Testing the changes done.

## BT_2358 IDAMSOA enhancements De
@Note:Don't delete older data from this sheet, It will track information specific to this project only.
Resource Name | Service Name | Task details | Task date | Task Hour
Sandeep | PVEmployee | 1.PVEmployee port access RFC testing. 2.Service testing for file publish on plan view server.3.RFC updation with file name changes issue. | 2019-02-13 | 3
Sandeep | PVEmployee | PVEmployee sub service changes | 2019-02-18 | 3
Sandeep | PVEmployee | PVEmployee sub service changes | 2019-02-19 | 2
Sandeep | PVEmployee | PVemployee service changes for column, deployment & testing in dev/test server | 2019-02-20 | 3
Shrikant | GSKIntegration | Undepolyed all the previous versions of services in dev Environment and clean up of old services i had created. | 2019-03-04 | 2
Shrikant | BiztalkIntegration | Helped tony redarding error in stored procedure for biztalk integration flow | 2019-03-04 | 4
Shrikant | WSO2 | handover wso2 administration scripts to shivang for furthur enhancements. | 2019-03-06 | 4
Shrikant | WSO2 | gone through ansible documentation for wso2 update automation | 2019-03-07 | 8
Kavindra | Business Rule | Going through business Rule. Demo scheduled for Friday. Working on presentation and POC. | 2019-04-04 | 2
Kavindra | Business Rule | Going through business Rule. Demo scheduled for Friday. Working on presentation and POC. | 2019-04-05 | 2
Sandeep | GemsFullLoad | Re-development of service from scratch with new design | 2019-04-05 | 8
Dharm | Apex Authentication & Authorization | Looking about Authentication & Authorization to use it in our apex application | 2019-04-02 | 3
Dharm | Apex Authentication & Authorization | Looking about Authentication & Authorization to use it in our apex application | 2019-04-03 | 3
DHARM | GEMS APEX | Working on GEMS apex UI changes for manage the entity and POA data. | 2019-04-04 | 8
DHARM | GEMS APEX | Working on GEMS apex UI changes for manage the entity and POA data. | 2019-04-05 | 8
Sandeep | GemsFullLoad | Re-development of service from scratch with new design | 2019-04-08 | 8
DHARM | GEMS APEX | Working on GEMS apex UI changes for manage the entity and POA data. | 2019-04-08 | 8
DHARM | GEMS APEX | Working on GEMS apex UI changes for manage the entity and POA data as well as Home Page. | 2019-04-09 | 8
Kavindra | Apex | Going through APEX UI and development process. | 2019-04-08 | 2
Kavindra | Apex | Working on cleanup activity , undeployed duplicate services from dev. Going through APEX development | 2019-04-09 | 6
Sandeep | GemsFullLoad | Gems service full load new service development | 2019-04-08 | 8
Sandeep | GemsFullLoad | Gems Full load service test server RFC work | 2019-04-09 | 2
Sandeep | GemsFullLoad | NEW Gems service production rfc NEW Gems service documentation | 2019-04-18
Kavindra | Apex | Exploring APEX documents and doing demo apps.Oracle® Application Express ,Tutorial: Building an Application | 2019-04-18 | 2
Kavindra | Apex | Exploring APEX documents and doing demo apps.Oracle® Application Express ,Tutorial: Building an Application | 2019-04-19 | 8
Kavindra | GIT SOA Projects | Pushed below services to GIT SOA. 1. SalesforceProduct 2. ICESheetToSalesforceIntegration 3. GRMSumTotal 4. ClearTrialIntegration 5. SSU_Integration 6. InvestigatorPortal | 2019-04-25 | 4
Sandeep | GemsFullLoad | GEMS service testing on prod, service documentation | 2019-04-23 | 2
Dharm | GEMS APEX | Working on GEMS apex UI changes for manage the home page information via admin page for contact, POA forms and Home Text. | 2019-04-24 | 4
Dharm | GEMS APEX | Working on GEMS apex UI changes for manage the home page information via admin page for contact, POA forms and Home Text. | 2019-04-25 | 4
Dharm | GEMS APEX | Working on GEMS apex UI changes for manage the home page information via admin page for contact, POA forms and Home Text. | 2019-04-26 | 3
Sandeep | GemsFullLoad | SOA GIT repo documentation uploading, Repo management, project clean up. GPG encryption work | 2019-04-26 | 8
Dharm | GEMS APEX | Working on GEMS apex UI changes for manage the home page information via admin page. | 2019-04-30 | 4
Dharm | GEMS APEX | Working on GEMS apex UI changes for manage the home page information via admin page for contact, POA forms and Home Text and designed. | 2019-05-02 | 6
Dharm | GEMS APEX | Working on GEMS apex UI changes for manage the home page information via admin page for contact, POA forms and Home Text. Worked on edit and delete button. | 2019-05-03 | 5

## Efforts_Hours
Month | 2019-10-01
Name | Total Working days | Employee working day | No Leaves | Working Hours
Shivang | 20 | 20 | 0 | 160
Malla | 20 | 19 | 1 | 152
Kanif Nath | 20 | 18 | 2 | 144
Shrikanth | 20 | 20 | 0 | 160
Sandeep | 20 | 20 | 0 | 160
Shashi | 20 | 19 | 1 | 152
Rama Shankar | 20 | 20 | 0 | 160
Shivam | 20 | 20 | 0 | 160
Simrat | 20 | 20 | 0 | 160

## ProjectCode
Sno | Project code
1 | SSU (1590)
2 | BT_1876 - SOA enhancements
3 | BT_184_L Veeve
4 | BT_2125 - SDTS-Enhancements & Config
5 | Legal entity Integration(BT_194L )
6 | BT_1855_L - Roche Data Integration
7 | BT_1856_L - CIF Replace/Decommission
8 | BT_2085 - SYNH Inform to GSK Coding SOA
9 | BT_277_L - Telecom Exp Mgmt (TEM)
10 | BT_1588 - Integrate iMedidata and CTMS : CAM II
11 | BT_1909_L - GAM Automation
12 | BT_201_L - GIPS Tooling -- Consolidated I-SNOW
BT_117_L - Enterprise Service Bus Rationa
BT_2062_L - Travel Mgmt Co. Consolidation-BCD
BT_2347 - Subject Data Transfer Services
BT BAU Small Enhancements - BT BAU Small Enhancements
BT_2085 - SYNH Inform to GSK Coding
BT_1380 - PV POD
BT_2358 - IDAM/SOA enhancements
BT_1600 - Contract Management Implementa-EBSINSIGHT INVOICE

## LastWeek_Backup
S.No | Project | Start Date | Completion Date | % Completion | Resource | Tasks Accomplished
1 | BT_201_L - GIPS Tooling -- Consolidated I |  |  |  | Sandeep | Documents SnowCreateIndex SnowUserSub SnowService with new OIM & OID Group changes.
2 | BT_184_L - Vault Config eTMF & Doc Gtwy |  |  |  | Sandeep | Veeva clinical OIM Audit and OID group add/delete process development. Veeva clinical OIM Audit and OID group add/delete process development. Code migration on GIT repo. Veeva clinical OIM Audit and OID group add/delete process development. testing of all scenarios, Procedure changes for OIM data
[5 empty] | Garima | Created Service Spec doc for :VeevaStudySub,VeevaStudyEventSub,VeevaCountryEventSub,VeevaStudyCountryStatusSub,VeevaStudyStatusSub Created fow chart for: Study Status, Country Event and Country Status Interfaces Shared PROD FTP Connection Details Added Study Inactive logic to VeevaStudySub
[5 empty] | Shashi | Specification document for below service 1. VeevaMilestoneOutboundSub 2.VeevaStudySiteStatusSub 3.DLMCTMSDataService 4.ETMFService Activity Diagram for below 1.Site Status Flow 2.Milestone Flow Changes done in VeevaStudySiteEventSub and VeevaSiteProfileEventSub due to Adhoc enhancement . End to end testing for all scenarios related to adhoc changes .
[5 empty] | Malla | Working on VeevaAdHocEvent service. Modified Below service as part of Enhencement. VeevaMilestoneEvent Service VeevaAdHocEvent Service VeevaVendorService VeevaProfileUpdate Service Modified PublishSiteMilestone XSLT for Uniq MilestoneId.
Venkat
3 | BT_2008_L - Ph 4 Enterprise CRM-Implement |  |  |  | Kavindra
4 | BT_2095 - Automate Processes-Gen Privacy |  |  |  | Sandeep
[5 empty] | Kavindra | 1. Raised RFC 3-94UBLK1: GDPR Integration Migration - Prod. Provided GDPR Artifacts.[Now RFC successfully executed earlier getting issue because of schema changed in PROD] 2. Fixed issue that we are getting while deploying the GDPR services on prod (RFC 3-94UBLK1). Changed the schema from EventMessage_v1.xsd to "ECS_EventMessage_v1.xsd". Deployed and tested on test environment after making change in service.
5 | BT_2001 - Master Data Management |  |  |  | Kavindra | 1. Done the necessary changes in procedure. Procedure is working fine, data is getting upsert into INVESTIGATOR table and IPInvestigatorPub [1.0] service is getting the data from IPDB database and sending to PRISM. Tested the Flow- Prism to IPDB and vice versa.
6 | BT_2347 - Subject Data Transfer Services |  |  |  | Dharm | Verified the RFC changes on test ENV and testing the existing Study. Worked on Missing data of Urovant Study and shared the report to client.
8 | BT_2358 - IDAM/SOA enhancements |  |  |  | Sandeep | NEW Gems service production rfc NEW Gems service documentation
[5 empty] | Shivang | 1. Did code enhacement for GSK standalone java processes for better exception handling and re-connect database issue for below processes. 1.1 GskCodingDownload 1.2 GskCodingProcessor 1.3 GskWsClient 1.4 GskGetPatientList 1.5 GskGetSiteList 2. Uploaded new changes on DEV and TEST, did successfull testing for overall cycle. 3. Looked into WSO2 installation and ansible script that were already there. 4. Started working on script for restarting services for WSO2 when server health is critical and sending email notification. Will continue on this next week.
Dharm
[5 empty] | Shrikant | 1. RoadMap for WSO2 updates in DA server. 2. Installing Required packages to get started with automated updates in DA server: 2.1 Installed GIT in DA DEV server 2.2 Installed Ansible in DA Dev server. 3. Documented the steps involved. 4. Configuring ansible and document to configure. 5. SSH issue to connect to the server resolution(Installed ssh private key for ansible hosted servers and added in configuration file)
9 | BT_2214 - Connect for Sites: MDM Align |  |  |  | Kavindra | Site Invoice Payments - Update with Reltio Id: Analyzed SitePayments services code and service flow , As per my analysis, below are my findings: 1. Changes will be required in SitePaymentdetSub Service. 2. reltio_id column need to add in nxsdDetailInvoice.xsd schema file. 3. reltio_id column need to add in DL_INVOICE_DETAILS DB table . 4. InsertDetailInvoice DB adapter need to update in code. 5. Mapping for reltio_id required in SitePaymentDetailInvoice.xsl transformation. As waiting for confirmation from Sri/Pavani for Column name, Done the necessary changes in my local.
10 | BT_1909_L - GAM Automation |  |  |  | Dharm | Working on GAM GUI issue and testing. Moving the changes to PROD app 150. Working on Admin user list page and functionality of it.
11 | BT_2008_L - Ph 4 Enterprise CRM-Implement |  |  |  | Kavindra
12 | BT_2008_L - Ph 4 Enterprise CRM-Implement |  |  |  | Malla | SalesForceApplication: Wprking on SFPickListService Working on SFPIckListValues Service Deployed in Dev and tested. Created RFC for Val deloyment.